## Sheet1
On track no concerns
Needs attention or rescheduling
Lack of progress and no plan in place
Task no. | Project and committee | Milestone at May 1st 2022 | Notes | Status | Lead Cllr | Lead Staff | Budget
Community Committee
1 | Community Development in Baildon | * Monitor and evaluate CD activities in 21/22 delivered by Baildon Link, St Hughes and Hale * Review priorities for 2022 onwards and agree new scheme by end of 2021 | This funding has been reviewed . Four Hubs, Baildon Community Link, St James, St Hughes and Wesley will each received a grant of £10,000 eachfor 22/23. |  | DR | Clerk /Dep | £40k
2 | Activities for young people in Baildon | * Monitor and evaluate activities in 21/22 delivered by Baildon Link (9=13 youth club) and Hale (Baildon Youth Council) * Review priorities for 2022 and agree new scheme by end of 2021 | This funding has also been reviewed and will be continued 22/23 at £10,000 each. |  | DR | Clerk/Dep | £21.5k
3 | Baildon Neighbourhood Watch / community safety | Continue to support NHW across Baildon and promote community involvement in all community safety issues | NHW continues to deliver across the whole Baildon Community a strong feeling of safety and security in partnership with local police neighbourhood teams. Funding supports crimestoppage. Also additional defibrillator at Sandals sports field. |  | MT | Clerk/Dep | £2.98k
4 | Skylark community grant scheme | Award small grants of up to £500 to local community projects Evaluate success of scheme by end of the year | Skylark applications continue to be popular and fund variety of community projects. |  | DR | RL | £3k
5 | Baildon Buddies | Evaluate project and review continuation from April 2022 | Review of budgets decided to discontinue this funding in favour of other community projects in 22/23. |  | DR | Clerk/Dep | £3k
Economy Committee
6 | Baildon Christmas lights | Annual schedule followed inc ordered with suppliers for 2022 by end of May. Positive display over Xmas 2021. Potted meat stick project implemented | 2021 plan executed. Order to be placed for 2022 with Christmas Plus. PMS lighting ongoing, may take longer. |  | PS GD | Clerk/MS | £8.4k
7 | Xmas events inc switch on if possible | Xmas co-ordination group convened and programme agreed and implemented | Planning for 2022 later in year |  | PS | Clerk/Dep | £1k
8 | Walkers are Welcome | Programme in place and agreed | Programme underway and being implemented |  | GD | N/A | 500
9 | Northgate Toilets / Love our Loos | Operating to high standard, all issues resolved. Grant application submitted for disabled loos and implemented. Love our Loos group fully involved | Love our loos group fully engaged. Plans for improvements to disabled facility in hand. |  | SH/GD | Clerk | £9k
10 | Harley rally | All events much reduced last weekend in August 2021 | Harley Rally confirmed to go ahead 2022. Dates to be confirmed |  | SP | N/A | £2.25k
11 | Baildon station improvements | Support for FoBS - projects for year agreed and in place | On going projects in place, but major one is dependent on Northern for timescale |  | GD | N/A | £1.9k
12 | Visit Baildon | Group engaged; website / digital offer operational | Website under construction and formal launch, date to be confirmed |  | SH | N/A
13 | Business support / BIG Chamber of Commerce | Post COVID relaunch of BIG a success and Baildon businesses engaged with Baildon issues | full meeting plan in place, 1st meeting was great success |  | SP | N/A | 500
14 | Baildon Literature Festival | Plans in place for 2022 festival | Planned for October this year dates to be confirmed |  | SP | N/A | TBC
Environment Committee
15 | Jenny Lane playground improvement project | Approval of upgrade by BDMC | Bradford MDC and Catholic have agreed for upgrade to proceed. |  | PS | N/A | BDMC financing
16 | Baildon reservoir | Legal matters in court concluded by BMDC and resolved. Future for site under discussion | Legal matters concluded in October 2021; Bradford MDC are owners |  | GD/PS | Clerk | None
17 | Baildon benches | Replacement / restoration of at least 50% of highway benches | All approved and programme launch imminent. Work likely in May 2022. |  | PS/GD | MS | £10k (£5k base + £5k cf)
18 | Grit bins | 100% provision and annual salt fill complete before winter | Annual salt fill completed |  | PS | MS | £4k
19 | Bracken Hall improvement project | Completed | Centre opening set for 02/04/22 |  | PS | Clerk /Dep | £11K
20 | Clean and Green, and Litter Free Baildon | Contract working well (C&G), volunteers active. Baildon well looked after | Underspend projected this year |  | PS | MS | £9k
21 | Baildon cycle track | Work started | Planning permission being sought |  | PS | N/A | TBC
Planning Committee
22 | Consideration & comment on all Baildon planning apps & tracking appeals | Ongoing | We are continuing to track and monitor specific planning applications as necessary and now have a spreadsheet to identify them as ongoing tasks. |  | SH | RL | Base
23 | Represent BTC in highway consultations with Bradford | Ongoing | Keep informed and monitor local road closures |  | SH | RL | Base
24 | Prepare a NDP for Baildon | Consultation underway | A consultant has been appointed and funds are being placed in reserve for NDP . Consultation planned for April 22. |  | GD/SH | RL | up to £5k + £10k grant
Governance Committee
25 | Ensure strong governance for BTC | Clear policy schedule all up to date. AGAR signed off | Majority up to date = expect to complete by year end . Agar not due yet |  | GD | Clerk | Base
26 | Strong financial management in place | Budget set for 2022/23 Financial operations meet policy standards and fin regs | All complete |  | GD | RFO | Base
27 | Secure foundation quality award | Application made and approved | DEFER. Not possible until Clerk has CILCA qualification |  | GD | Dep Clerk | 146
28 | Temp/perm office space for BTC secured | Office base secure for at least 12 months | Good progress with both temp and permanent plans for Offices. Permanent office estimated 2023 |  | GD | Clerk | TBC
29 | Temp/perm location for library secured | Library in new location and fully operational | Good progress with temp and permanent locations. Permanent library est 2023 |  | GD | Clerk | BDMC
30 | Progress made in partnership with Bradford on redevelopment of Bradford Council's ICH site | Redevelopment plan agreed with Bradford, including appropriate consultation | Progress made with Bradford Council decisions re 28 and 29. Redevelopment process unlikely to start until 2022/23 |  | GD | Clerk | Base
31 | Good communication between BTC and residents of Baildon | Newsletter performance increased Social media performance increased Increased face to face engagement | Stats needed . Face to face engagement limited by COVID, but stall at Farmers market continues |  | GD | Clerk | Base
32 | Good workforce and succession planning | Policies in place and regular reviews as needed | Major staff changes this year. Organisation review due in 2022/23 |  | GD | Clerk | Base